## Team
Project Team Details
Initial | First Name | Last Name | Email | GitHub Username
PM | Prashant | Mall | pmall@stevens.edu | prashantmall1997
MS | Mrunal | Salunke | msalunk3@stevens.edu | mrunal2021
SS | Shubhangi | Sharma | ssharm21@stevens.edu | shubhangi9722
SM | Seema | Muchandi | smuchand@stevens.edu | Seema1101
|  |  | GitHub Repository: | CS555-AgileProject-Group2

## Backlog
Backlog Details
Sprint | Story ID | Owner | Story Name | Status
2 | US09 | MS | Birth before death of parents | Testing
| T09 |  | Implementation and Integration of User Story 9 where birth date should be before the death date of either parents
2 | US10 | MS | Marriage after 14 | Testing
| T10 |  | Implementing User Story 10 where the marriage date should not be before the age of 14
2 | US11 | PM | No bigamy | Testing
| T11 |  | Compare and implement the current marriage date which should not appear before any of the previous marriage date of either spouses
2 | US12 | PM | Parents not too old | Testing
| T12.01 |  | Store children birth date
| T12.02 |  | Compare and implementing birth date of mother less than 60 years of that of children birth date
| T12.03 |  | Compare and implementing birth date of father less than 80 years of that of children birth date
2 | US13 | SM | Siblings spacing | Testing
| T13.01 |  | Store birth date of siblings more than 8 months apart
| T13.02 |  | Store birth date of siblings less than 2 days apart (for twins)
| T13.03 |  | Compare and implementing the birth dates of siblings
2 | US14 | SM | Multiple births <= 5 | Testing
| T14.01 |  | Store the number of siblings which should not be more than 5
| T14.02 |  | Compare and implementing the birth dates of siblings
2 | US15 | SS | Fewer than 15 siblings | Testing
| T15.01 |  | Store the number of siblings not more than 15
2 | US16 | SS | Male last names | Testing
| T16.01 |  | Store the last name of the family
| T16.02 |  | Compare and implementing the last name of the male members
3 | US09 | MS | No marriages to descendants | Coding
3 | US10 | MS | Siblings should not marry | Coding
3 | US11 | PM | First cousins should not marry | Coding
3 | US12 | PM | Aunts and uncles | Coding
3 | US13 | SM | Correct gender for role | Coding
3 | US14 | SM | Unique IDs | Coding
3 | US15 | SS | Unique name and birthdate | Coding
3 | US16 | SS | Unique families by spouses | Coding

## Burndown
Burndown Chart for Competed Sprints and Remaining Stories
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 03-01-2021 | 32 |  | 0
Sprint 1 | 03-17-2021 | 24 | 8 | 190 | 300 | 38
Sprint 2 | 03-29-2021 | 16 | 8 | 434 | 325 | 80.07

## Sprint 2
Completed Sprint 2 User Stories
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US09 | Birth before death of parents | MS | Done | 60 | 60 | 40 | 60 | 03/29/2021
US10 | Marriage after 14 | MS | Done | 30 | 60 | 22 | 60 | 03/29/2021
US11 | No bigamy | PM | Done | 70 | 80 | 85 | 78 | 03/29/2021
US12 | Parents not too old | PM | Done | 130 | 128 | 60 | 63 | 03/29/2021
US13 | Siblings spacing | SM | Done | 45 | 60 | 66 | 34 | 03/29/2021
US14 | Multiple births <= 5 | SM | Done | 60 | 20 | 68 | 10 | 03/29/2021
US15 | Fewer than 15 siblings | SS | Done | 10 | 10 | 5 | 5 | 03/29/2021
US16 | Male last names | SS | Done | 30 | 30 | 20 | 15 | 03/29/2021
Review Results
Keep Doing:
Bring pizza to our meetings
Bring silverware for everyone
Avoid:
Leaving leftover pizza on the counter

## Sprint 3
Overview of Sprint 3
Sprint | Story ID | Owner | Story Name | Status
3 | US17 | SS | No marriages to descendants | Coding
3 | US18 | SS | Siblings should not marry | Coding
3 | US19 | MS | First cousins should not marry | Coding
3 | US20 | MS | Aunts and uncles | Coding
3 | US21 | PM | Correct gender for role | Coding
3 | US22 | PM | Unique IDs | Coding
3 | US23 | SM | Unique name and birthdate | Coding
3 | US24 | SM | Unique families by spouses | Coding