## Sprint 1
Completed Sprint 1 User Stories
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | Dates before current date | PM | Done | 30 | 60 | 31 | 25 | 2021-03-17
T01.01 | Store Current date | PM
T02.02 | Store Birth, Marriage and Divorce dates | PM
T03.03 | Compare Birth, Marriage and Divorce dates with the current date | PM
US02 | Birth before marriage | PM | Done | 30 | 60 | 22 | 30 | 2021-03-17
T02.01 | Store Birth date | PM
T02.02 | Store Marriage date after Birth date | PM
US03 | Birth before death | SM | Done | 30 | 60 | 17 | 20 | 2021-03-17
T03.01 | Store Birth date | SM
T03.02 | Store Death date | SM
T03.03 | Compare Birth and Death dates | SM
US04 | Marriage before divorce | SM | Done | 30 | 60 | 22 | 30 | 2021-03-17
T04.01 | Store Divorce date of either spouses | SM
T04.02 | Store Marriage date of the spouses before Divorce date | SM
T04.03 | Store Divorce date after Marriage date | SM
US05 | Marriage before death | SS | Done | 30 | 60 | 18 | 45 | 2021-03-17
T05.01 | Find Marriage record for an individual | SS
T05.02 | Find Marriage date | SS
T05.03 | Compare Marriage date to Birth date | SS
US06 | Divorce before death | SS | Done | 30 | 60 | 20 | 60 | 2021-03-17
T06.01 | Store Death date of Husband | SS
T06.02 | Store Death date of Wife | SS
T06.03 | Store Divorce date before death dates of Spouses | SS
US07 | Less then 150 years old | MS | Done | 30 | 60 | 35 | 30 | 2021-03-17
T07.01 | Store Death date of dead people less than 150 years | MS
T07.02 | Store Birth date of people | MS
T07.03 | Current date should be less than 150 years after birth date | MS
US08 | Birth before marriage of parents | MS | Done | 30 | 60 | 25 | 60 | 2021-03-17
T08.01 | Store Marriage date | MS
T08.02 | Store Divorce date | MS
T08.03 | Child's birth date should fall between Marriage date and 9 months after divorce date | MS
Review Results
Keep Doing:
Bring pizza to our meetings
Bring silverware for everyone
Avoid:
Leaving leftover pizza on the counter