## Sheet1
Initial | First Name | Last Name | Email | GitHub Username
PM | Prashant | Mall | pmall@stevens.edu | prashantmall1997
MS | Mrunal | Salunke | msalunk3@stevens.edu | mrunal2021
SS | Shubhangi | Sharma | ssharm21@stevens.edu | shubhangi9722
SM | Seema | Muchandi | smuchand@stevens.edu | Seema1101
|  |  | GitHub Repository: | CS555-AgileProject-Group2
Sprint | Story ID | Owner | Story Name | Status
1 | US01 | PM | Dates before currennt date | Coding
1 | US02 | PM | Birth before marriage | Coding
1 | US03 | SM | Birth before death | Coding
1 | US04 | SM | Marriage before divorce | Coding
1 | US05 | SS | Marriage before death | Coding
1 | US06 | SS | Divorce before death | Coding
1 | US07 | MS | Less then 150 years old | Coding
1 | US08 | MS | Birth before marriage of parents | Coding

## Sheet2
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 03-01-2021 | 32 |  | 0
Sprint 1 | 03-17-2021 | 24 | 8 | 240 | 480

## Sheet3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | Dates before current date | PM | Coding | 30 | 60
US02 | Birth before marriage | PM | Coding | 30 | 60
US03 | Birth before death | SM | Coding | 30 | 60
US04 | Marriage before divorce | SM | Coding | 30 | 60
US05 | Marriage before death | SS | Coding | 30 | 60
US06 | Divorce before death | SS | Coding | 30 | 60
US07 | Less then 150 years old | MS | Coding | 30 | 60
US08 | Birth before marriage of parents | MS | Coding | 30 | 60