## Team
Project Team Details
Initial | First Name | Last Name | Email | GitHub Username
PM | Prashant | Mall | pmall@stevens.edu | prashantmall1997
MS | Mrunal | Salunke | msalunk3@stevens.edu | mrunal2021
SS | Shubhangi | Sharma | ssharm21@stevens.edu | shubhangi9722
SM | Seema | Muchandi | smuchand@stevens.edu | Seema1101
|  |  | GitHub Repository: | CS555-AgileProject-Group2

## Backlog
Backlog Details
Sprint | Story ID | Owner | Story Name | Status
4 | US28 | SM | Order siblings by age | Done
4 | US29 | SM | List deceased | Done
4 | US30 | SS | List living married | Done
4 | US31 | SS | List living single | Done
4 | US33 | MS | List orphans | Done
4 | US38 | MS | List upcoming birthdays | Done
4 | US39 | PM | List upcoming anniversaries | Done
4 | US42 | PM | Reject illegitimate dates | Done

## Burndown
Burndown Chart for Competed Sprints and Remaining Stories
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 03-01-2021 | 32 |  | 0
Sprint 1 | 03-17-2021 | 24 | 8 | 190 | 300 | 38
Sprint 2 | 03-29-2021 | 16 | 8 | 434 | 325 | 80.07
Sprint 3 | 04-14-2021 | 8 | 8 | 216 | 215 | 60.2791
Sprint 4 | 04-28-2021 | 0 | 8 | 288 | 313 | 55.2073

## Sprint 4
Completed Sprint 4 User Stories
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US28 | Order siblings by age | SM | Done | 60 | 50 | 44 | 40 | 04/26/2021
T28.01 | Store age of siblings in the family | SM
T28.02 | Store the age by desending order | SM
US29 | List deceased | SM | Done | 30 | 5 | 23 | 3 | 04/26/2021
T29.01 | Store the death date of each individual who died | SM
US30 | List living married | SS | Done | 15 | 15 | 16 | 15 | 04/26/2021
T30.01 | Store the names of the people married in the family | SS
T30.02 | Store the date of marriage and date of birth of each individual | SS
T30.03 | Compare and check birth dates and death dates of people who are married | SS
US31 | List living single | SS | Done | 15 | 15 | 16 | 15 | 04/26/2021
T31.01 | Store all the names and age in the GEDCOM file | SS
T31.02 | Store their birth days and check if their age is above 30 | SS
T31.03 | Check if they are unmarried | SS
US33 | List orphans | MS | Done | 35 | 20 | 31 | 30 | 04/26/2021
T33.01 | Store the children names | MS
T33.02 | Store their birth dates and compare for their age should be < 18 | MS
T33.03 | Store the names of the parents | MS
T33.04 | Store their birthdate and their death date | MS
US38 | List upcoming birthdays | MS | Done | 40 | 60 | 34 | 90 | 04/26/2021
T38.01 | Store the upcoming birth date of each individual | MS
US39 | List upcoming anniversaries | PM | Done | 35 | 30 | 39 | 30 | 04/26/2021
T39.01 | Store the marriage date of each living couple in a GEDCOM file | PM
T39.02 | Compare if the dates occur in the next 30 days | PM
US42 | Reject illegitimate dates | PM | Done | 90 | 120 | 85 | 90 | 04/26/2021
T42.01 | Store the dates in a legititmate format | PM
T42.02 | Compare the stored dates if they are illegitimate | PM
Review Results
Keep Doing:
Bring pizza to our meetings
Bring silverware for everyone
Avoid:
Leaving leftover pizza on the counter