## Team
Project Team Details
Initial | First Name | Last Name | Email | GitHub Username
PM | Prashant | Mall | pmall@stevens.edu | prashantmall1997
MS | Mrunal | Salunke | msalunk3@stevens.edu | mrunal2021
SS | Shubhangi | Sharma | ssharm21@stevens.edu | shubhangi9722
SM | Seema | Muchandi | smuchand@stevens.edu | Seema1101
|  |  | GitHub Repository: | CS555-AgileProject-Group2

## Backlog
Backlog Details
Sprint | Story ID | Owner | Story Name | Status
4 | US28 | SM | Order siblings by age | Coding
4 | US29 | SM | List deceased | Coding
4 | US30 | SS | List living married | Coding
4 | US31 | SS | List living single | Coding
4 | US33 | MS | List orphans | Coding
4 | US38 | MS | List upcoming birthdays | Coding
4 | US39 | PM | List upcoming anniversaries | Coding
4 | US42 | PM | Reject illegitimate dates | Coding

## Burndown
Burndown Chart for Competed Sprints and Remaining Stories
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 03-01-2021 | 32 |  | 0
Sprint 1 | 03-17-2021 | 24 | 8 | 190 | 300 | 38
Sprint 2 | 03-29-2021 | 16 | 8 | 434 | 325 | 80.07
Sprint 3 | 04-14-2021 | 8 | 8 | 216 | 215 | 60.2791

## Sprint 3
Completed Sprint 3 User Stories
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US21 | Correct gender for role | SS | Done | 25 | 10 | 22 | 10 | 04/13/2021
T21.01 | Store husband gender | SS
T21.02 | Store Wife gender | SS
T21.03 | Compare the gender of spouses | SS
US22 | Unique IDs | SS | Done | 45 | 30 | 39 | 30 | 04/13/2021
T22.01 | Store Individual ID | SS
T22.02 | Store Family IDs and Check if they are unique | SS
US23 | Unique name and birthdate | MS | Done | 40 | 40 | 34 | 30 | 04/13/2021
T23.01 | Store Individual name | MS
T23.02 | Store Individual birth date | MS
T23.03 | Compare and check names and birth dates should not be same | MS
US24 | Unique families by spouses | MS | Done | 40 | 40 | 34 | 30 | 04/13/2021
T24.01 | Store spouse names and marriage dates
T24.02 | Compare so that not more than one family should have same spouse by name and marriage date | MS
US25 | Unique first names in families | PM | Done | 45 | 60 | 41 | 45 | 04/13/2021
T25.01 | Store the children names | PM
T25.02 | Store their birth dates and compare for they should not match | PM
US27 | Include individual ages | PM | Done | 10 | 20 | 8 | 10 | 04/13/2021
T27.01 | Store Individuals current age | PM
US35 | List recent births | SM | Done | 20 | 30 | 18 | 30 | 04/13/2021
T35.01 | Store the birth date of each individual in the last 30 days | SM
T35.02 | Check the birth dates | SM
US36 | List recent deaths | SM | Done | 20 | 30 | 20 | 30 | 04/13/2021
T36.01 | Store the death date of each individual who died in the last 30 days | SM
T36.02 | Check the death dates | SM
Review Results
Keep Doing:
Bring pizza to our meetings
Bring silverware for everyone
Avoid:
Leaving leftover pizza on the counter

## Sprint 4
Overview of Sprint 4
Sprint | Story ID | Owner | Story Name | Status
4 | US28 | SM | Order siblings by age | Coding
4 | US29 | SM | List deceased | Coding
4 | US30 | SS | List living married | Coding
4 | US31 | SS | List living single | Coding
4 | US33 | MS | List orphans | Coding
4 | US38 | MS | List upcoming birthdays | Coding
4 | US39 | PM | List upcoming anniversaries | Coding
4 | US42 | PM | Reject illegitimate dates | Coding