## Team
Project Team Details
Initial | First Name | Last Name | Email | GitHub Username
PM | Prashant | Mall | pmall@stevens.edu | prashantmall1997
MS | Mrunal | Salunke | msalunk3@stevens.edu | mrunal2021
SS | Shubhangi | Sharma | ssharm21@stevens.edu | shubhangi9722
SM | Seema | Muchandi | smuchand@stevens.edu | Seema1101
|  |  | GitHub Repository: | CS555-AgileProject-Group2

## Backlog
Sprint | Story ID | Owner | Story Name | Status
1 | US01 | PM | Dates before currennt date | Done
1 | US02 | PM | Birth before marriage | Done
1 | US03 | SM | Birth before death | Done
1 | US04 | SM | Marriage before divorce | Done
1 | US05 | SS | Marriage before death | Done
1 | US06 | SS | Divorce before death | Done
1 | US07 | MS | Less then 150 years old | Done
1 | US08 | MS | Birth before marriage of parents | Done

## Burndown
Burndown Chart for Competed Sprints and Remaining Stories
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 03-01-2021 | 32 |  | 0
Sprint 1 | 03-17-2021 | 24 | 8 | 190 | 300 | 38

## Sprint1
Completed Sprint 1 User Stories
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | Dates before current date | PM | Done | 30 | 60 | 31 | 25 | 03/17/2021
T01.01 | Store Current date | PM
T02.02 | Store Birth, Marriage and Divorce dates | PM
T03.03 | Compare Birth, Marriage and Divorce dates with the current date | PM
US02 | Birth before marriage | PM | Done | 30 | 60 | 22 | 30 | 03/17/2021
T02.01 | Store Birth date | PM
T02.02 | Store Marriage date after Birth date | PM
US03 | Birth before death | SM | Done | 30 | 60 | 17 | 20 | 03/17/2021
T03.01 | Store Birth date | SM
T03.02 | Store Death date | SM
T03.03 | Compare Birth and Death dates | SM
US04 | Marriage before divorce | SM | Done | 30 | 60 | 22 | 30 | 03/17/2021
T04.01 | Store Divorce date of either spouses | SM
T04.02 | Store Marriage date of the spouses before Divorce date | SM
T04.03 | Store Divorce date after Marriage date | SM
US05 | Marriage before death | SS | Done | 30 | 60 | 18 | 45 | 03/17/2021
T05.01 | Find Marriage record for an individual | SS
T05.02 | Find Marriage date | SS
T05.03 | Compare Marriage date to Birth date | SS
US06 | Divorce before death | SS | Done | 30 | 60 | 20 | 60 | 03/17/2021
T06.01 | Store Death date of Husband | SS
T06.02 | Store Death date of Wife | SS
T06.03 | Store Divorce date before death dates of Spouses | SS
US07 | Less then 150 years old | MS | Done | 30 | 60 | 35 | 30 | 03/17/2021
T07.01 | Store Death date of dead people less than 150 years | MS
T07.02 | Store Birth date of people | MS
T07.03 | Current date should be less than 150 years after birth date | MS
US08 | Birth before marriage of parents | MS | Done | 30 | 60 | 25 | 60 | 03/17/2021
T08.01 | Store Marriage date | MS
T08.02 | Store Divorce date | MS
T08.03 | Child's birth date should fall between Marriage date and 9 months after divorce date | MS
Review Results
Keep Doing:
Bring pizza to our meetings
Bring silverware for everyone
Avoid:
Leaving leftover pizza on the counter

## Sprint2
Overview of Sprint 2
Sprint | Story ID | Owner | Story Name | Status
2 | US09 | MS | Birth before death of parents | Coding
2 | US10 | MS | Marriage after 14 | Coding
2 | US11 | PM | No bigamy | Coding
2 | US12 | PM | Parents not too old | Coding
2 | US13 | SM | Siblings spacing | Coding
2 | US14 | SM | Multiple births <= 5 | Coding
2 | US15 | SS | Fewer than 15 siblings | Coding
2 | US16 | SS | Male last names | Coding

## Sheet3
Backlog Details